## Risk Register
Risk ID | Risk Title | Risk Category | Business Area | Owner | Likelihood (1-5) | Impact (1-5) | Risk Score | Rating | Status | Treatment | Due Date | Residual Score | Notes
R-001 | Unauthorized access to employee accounts | Cybersecurity | IAM | IAM Manager | 5 | 5 |  |  | Open | Mitigate | 2026-10-30 | 12 | Strengthen MFA and privileged access controls.
R-002 | Customer data exposure | Data Privacy | Security | CISO | 4 | 5 |  |  | In Progress | Mitigate | 2026-11-15 | 10 | Improve data classification and DLP monitoring.
R-003 | Ransomware disruption | Cybersecurity | IT/Security | Security Operations | 4 | 5 |  |  | In Progress | Mitigate | 2026-12-15 | 8 | Harden endpoints and validate recovery procedures.
R-004 | Third-party security incident | Third-Party | Vendor Management | GRC Manager | 4 | 4 |  |  | Open | Mitigate | 2026-11-30 | 9 | Require security attestations and remediation tracking.
R-005 | Delayed incident detection | Cybersecurity | SOC | SOC Manager | 3 | 5 |  |  | In Progress | Mitigate | 2026-10-31 | 8 | Improve SIEM coverage and alert triage.
R-006 | Excessive user privileges | IAM | Technology | IAM Manager | 4 | 4 |  |  | Open | Mitigate | 2026-11-10 | 8 | Perform quarterly access recertification.
R-007 | Incomplete asset inventory | Technology | IT Operations | IT Manager | 3 | 4 |  |  | Open | Mitigate | 2026-12-01 | 7 | Establish authoritative asset inventory.
R-008 | Delayed regulatory reporting | Compliance | Legal/Compliance | Compliance Officer | 2 | 4 |  |  | In Progress | Mitigate | 2027-01-15 | 5 | Formalize regulatory reporting workflow.
R-009 | Security awareness gaps | Human Risk | Enterprise | HR / Security | 3 | 3 |  |  | In Progress | Mitigate | 2026-11-30 | 5 | Refresh phishing and security awareness training.
R-010 | Backup recovery failure | Resilience | IT Operations | Infrastructure Manager | 2 | 5 |  |  | Open | Mitigate | 2026-12-20 | 6 | Test backups and document recovery evidence.

## Executive Dashboard
GRC Risk Dashboard
Maple Financial Services — Simulated Portfolio Dashboard
Total Risks |  | Critical Risks | High Risks | Open Risks
Risk Rating
Rating | Count
Critical
High
Medium
Low
Risk Status
Status | Count
Open
In Progress
Mitigated
Accepted
Closed
Management Focus
• Prioritize remediation of critical IAM, data exposure, and ransomware risks.
• Track high-risk third-party and privileged-access issues to closure.
• Use residual risk to determine whether remediation has reduced exposure.
• Review overdue actions and risk acceptance decisions at governance meetings.

## Methodology
Step | Description
1. Identify | Document the risk, affected business area, and accountable owner.
2. Assess | Score likelihood and impact on a 1–5 portfolio scale.
3. Prioritize | Calculate inherent risk score as likelihood × impact and assign a rating.
4. Treat | Select mitigation, acceptance, transfer, or avoidance.
5. Track | Monitor status, due dates, owners, and residual risk.
6. Report | Summarize material risks and remediation progress for management.

## Project Scope
Field | Value
Organization | Maple Financial Services (fictional)
Industry | Financial Services
Employees | 500
Project Type | Simulated enterprise GRC risk dashboard
Scope | Cybersecurity, technology, data privacy, IAM, third-party, resilience, compliance, and human risk
Out of Scope | Real organizational data, real customer information, production systems
Risk Scoring | Likelihood (1–5) × Impact (1–5); scoring model is a portfolio methodology and is not prescribed by a specific framework.

## References
Reference | Purpose
Portfolio methodology | Risk scoring, status, and dashboard metrics are simulated for demonstration.
NIST Cybersecurity Framework 2.0 | General cybersecurity risk-management context.
ISO/IEC 27001:2022 | Information-security management context.
Note | This dashboard does not represent a certification audit or real organization.