## Executive Dashboard
IAM Access Review — Executive Dashboard
Records Reviewed | Executive Summary
Critical Findings | The simulated review identified lifecycle, privileged-access, SoD, and contractor-access exceptions requiring remediation.
High Findings
SoD Conflicts
Privileged Accounts

## Access Review
Review ID | User / Role | Department | System | Access Level | Business Justification | Last Review Date | Manager Approval | MFA | Privileged? | SoD Conflict? | Finding | Risk | Recommended Action | Owner | Due
AR-001 | User-001 | Finance | Core Banking | Standard | Finance operations | 2026-08-15 | Approved | Enabled | No | No | No issue | Low | Retain access | Finance Manager | Next review
AR-002 | User-002 | Finance | Core Banking | Privileged | System administration | 2026-08-15 | Approved | Enabled | Yes | Yes | Privileged access conflicts with transaction approval responsibility | Critical | Remove conflicting entitlement and separate duties | IAM / Finance | 0-30 days
AR-003 | User-003 | Customer Support | CRM | Standard | Customer support | 2026-08-15 | Approved | Enabled | No | No | No issue | Low | Retain access | Support Manager | Next review
AR-004 | User-004 | IT | Cloud Platform | Admin | Cloud administration | 2026-08-15 | Approved | Enabled | Yes | Yes | Broad administrative access exceeds documented job requirement | High | Reduce role scope and enforce just-in-time privileged access | IAM / Cloud | 0-30 days
AR-005 | User-005 | HR | HRIS | Standard | HR operations | 2026-08-15 | Pending | Enabled | No | No | Manager approval not current | Medium | Obtain manager recertification | HR / IAM | 0-30 days
AR-006 | User-006 | Marketing | CRM | Standard | Marketing campaigns | 2026-08-15 | Approved | Enabled | No | No | No issue | Low | Retain access | Marketing Manager | Next review
AR-007 | User-007 | Finance | ERP | Standard | Financial reporting | 2026-08-15 | Approved | Enabled | No | Yes | User retains conflicting create/approve permissions | High | Remove approval entitlement and validate SoD | IAM / Finance | 0-30 days
AR-008 | User-008 | IT | Endpoint Management | Admin | Endpoint administration | 2026-08-15 | Approved | Enabled | Yes | No | No issue | Medium | Retain with quarterly privileged review | IT Manager | Next review
AR-009 | User-009 | Former Employee | CRM | Standard | No current business need | 2026-08-15 | N/A | Enabled | No | No | Terminated user account remains active | Critical | Disable account immediately and investigate deprovisioning control | IAM / HR | Immediate
AR-010 | User-010 | Contractor | Cloud Platform | Standard | Project support | 2026-08-15 | Approved | Enabled | No | No | Contract end date is not reflected in access record | High | Set expiry date and verify sponsor approval | IAM / Vendor Mgmt | 0-30 days
AR-011 | User-011 | Security | SIEM | Admin | Security monitoring | 2026-08-15 | Approved | Enabled | Yes | No | No issue | Medium | Retain with enhanced logging and quarterly review | SOC | Next review
AR-012 | User-012 | Finance | ERP | Standard | Accounts payable | 2026-08-15 | Approved | Enabled | No | No | No issue | Low | Retain access | Finance Manager | Next review

## Access Risk Register
Risk ID | Risk | Likelihood (1-5) | Impact (1-5) | Score | Rating | Treatment | Owner | Timeframe | Scoring Note
IAM-R01 | Former employee account remains active | 5 | 5 |  |  | Mitigate | IAM / HR | Immediate | Likelihood × Impact is a portfolio methodology used for this simulation; it is not prescribed by a specific IAM standard.
IAM-R02 | Privileged access creates segregation-of-duties conflict | 4 | 5 |  |  | Mitigate | IAM / Finance | 0-30 days
IAM-R03 | Excessive cloud administrator permissions | 4 | 4 |  |  | Mitigate | IAM / Cloud | 0-30 days
IAM-R04 | Contractor access lacks defined expiration | 3 | 4 |  |  | Mitigate | IAM / Vendor Mgmt | 0-30 days
IAM-R05 | Access recertification evidence is incomplete | 3 | 3 |  |  | Mitigate | IAM / Managers | 31-60 days

## Remediation Plan
Action ID | Finding | Remediation Action | Owner | Priority | Timeframe | Success Measure
IAM-A01 | Active former-employee account | Disable account, review authentication activity, validate offboarding workflow and document closure. | IAM / HR | Critical | Immediate | Account disabled and offboarding evidence completed.
IAM-A02 | SoD conflict in privileged access | Remove conflicting entitlement and establish independent approval/review. | IAM / Finance | Critical | 0-30 days | Conflicting entitlement removed and SoD check passed.
IAM-A03 | Excessive cloud admin access | Reduce role scope and implement just-in-time privileged access where feasible. | IAM / Cloud | High | 0-30 days | Admin role limited to documented responsibilities.
IAM-A04 | Contractor access lacks expiry | Add contract end dates, sponsor ownership and automated expiration. | IAM / Vendor Mgmt | High | 0-30 days | All sampled contractor accounts have valid expiry dates.
IAM-A05 | Incomplete recertification evidence | Standardize quarterly access certification and retain manager approval evidence. | IAM / Managers | Medium | 31-60 days | 100% of sampled reviews have current approval evidence.

## Scope & Methodology
Field | Value
Project | IAM Access Review
Organization | Maple Financial Services
Population | 12 simulated user/access records
Systems | Core Banking, ERP, CRM, HRIS, Cloud Platform, Endpoint Management, SIEM
Review Objective | Validate business need, manager approval, authentication, privileged access, segregation of duties and lifecycle controls.
Methodology | Review sample access records; compare role/access to stated business need; identify exceptions; rate risk; assign remediation owners and timeframes.
Important Note | This is a simulated portfolio project. All users, systems, approvals, dates, findings and risks are fictional. It is not a real production access review.

## Control Mapping
Control / Practice | Purpose | Evidence Reviewed | Assessment Result
Least Privilege | Limit access to what users need for their role. | Role/access record and business justification | Exceptions identified
Access Recertification | Ensure access remains appropriate over time. | Manager approval and review date | Approval gaps identified
MFA | Reduce authentication risk for sensitive access. | MFA status | Enabled for sampled users
Privileged Access Management | Restrict and monitor administrative access. | Privileged flag and role scope | Excessive access identified
Segregation of Duties | Prevent conflicting responsibilities. | SoD conflict indicator | Multiple conflicts identified
Joiner/Mover/Leaver | Ensure access changes with employment status. | Employment status and access state | Former employee account identified
Third-Party Access | Control contractor/vendor access lifecycle. | Contractor status and expiry | Expiry gap identified

## References
Source / Practice | Reference | Purpose
NIST | NIST SP 800-53 Rev. 5 — Access Control (AC) | Reference for access-control concepts and controls.
NIST | NIST SP 800-63B — Authentication and Lifecycle Management | Reference for digital identity and authentication concepts.
ISO | ISO/IEC 27001:2022 — Annex A | Reference for access control and identity-related information-security controls.