## Assessment
Function | Category | Outcome ID | NIST CSF Outcome | Current State | Target State | Gap? | Priority | Recommendation | Owner
Govern | Organizational Context | GV.OC-01 | Critical business services and stakeholders are identified | Partially Implemented | Fully Implemented | Yes | High | Define and document critical services, stakeholders, regulatory requirements and dependencies. | GRC
Govern | Risk Management Strategy | GV.RM-01 | Risk objectives are established and communicated | Partially Implemented | Fully Implemented | Yes | High | Formalize enterprise cybersecurity risk appetite and communicate it to business owners. | GRC
Govern | Roles, Responsibilities & Authorities | GV.RR-02 | Cybersecurity roles and responsibilities are coordinated and communicated | Partially Implemented | Fully Implemented | Yes | High | Document RACI for cybersecurity risk ownership and control responsibilities. | GRC
Govern | Policy | GV.PO-01 | Cybersecurity policy is established and communicated | Implemented | Implemented | No | Low | Continue annual policy review and maintain evidence of employee acknowledgement. | GRC
Govern | Oversight | GV.OV-01 | Cybersecurity risk outcomes are reviewed by appropriate leadership | Partially Implemented | Fully Implemented | Yes | Medium | Establish quarterly executive risk reporting with defined KRIs and remediation tracking. | CISO
Identify | Asset Management | ID.AM-01 | Assets are inventoried and managed | Partially Implemented | Fully Implemented | Yes | High | Create centralized asset inventory covering cloud, applications, endpoints and critical data stores. | IT
Identify | Risk Assessment | ID.RA-01 | Vulnerabilities and threats are identified | Partially Implemented | Fully Implemented | Yes | High | Establish recurring vulnerability and threat assessments with documented ownership. | Security
Identify | Improvement | ID.IM-01 | Improvements are identified from assessments and lessons learned | Partially Implemented | Fully Implemented | Yes | Medium | Create a formal improvement backlog tied to audit findings, incidents and risk assessments. | GRC
Protect | Identity Management | PR.AA-01 | Identities and credentials are managed | Partially Implemented | Fully Implemented | Yes | Critical | Implement centralized IAM lifecycle controls and automated joiner/mover/leaver workflows. | IAM
Protect | Authentication | PR.AA-03 | Users, services and devices are authenticated | Partially Implemented | Fully Implemented | Yes | Critical | Enforce MFA for privileged and remote access and expand coverage to high-risk applications. | IAM
Protect | Access Control | PR.AA-05 | Access permissions are defined, managed and reviewed | Partially Implemented | Fully Implemented | Yes | High | Implement quarterly access certifications and least-privilege reviews. | IAM
Protect | Awareness & Training | PR.AT-01 | Personnel receive cybersecurity awareness training | Implemented | Implemented | No | Low | Maintain annual awareness training and track completion. | HR/Security
Protect | Data Security | PR.DS-01 | Data-at-rest is protected | Partially Implemented | Fully Implemented | Yes | High | Verify encryption coverage for critical databases, backups and cloud storage. | Security
Protect | Technology Infrastructure | PR.IR-01 | Networks and technology infrastructure are protected | Partially Implemented | Fully Implemented | Yes | High | Standardize secure configuration baselines and monitor exceptions. | IT
Detect | Continuous Monitoring | DE.CM-01 | Networks and systems are monitored | Partially Implemented | Fully Implemented | Yes | High | Expand centralized logging and security monitoring across critical systems. | SOC
Detect | Adverse Event Analysis | DE.AE-02 | Potentially adverse events are analyzed | Partially Implemented | Fully Implemented | Yes | High | Define alert triage procedures, severity criteria and investigation SLAs. | SOC
Respond | Incident Management | RS.MA-01 | Incident response plan is executed | Implemented | Implemented | No | Low | Maintain and exercise the incident response plan annually. | Security
Respond | Incident Reporting | RS.CO-02 | Internal and external incident reporting requirements are established | Partially Implemented | Fully Implemented | Yes | Medium | Document escalation paths, regulatory notification requirements and reporting responsibilities. | Legal/Security
Respond | Mitigation | RS.MI-01 | Incidents are contained and mitigated | Partially Implemented | Fully Implemented | Yes | High | Define containment playbooks for ransomware, credential compromise and data exfiltration. | SOC
Recover | Incident Recovery Plan | RC.RP-01 | Recovery plans are executed | Partially Implemented | Fully Implemented | Yes | High | Test recovery procedures for critical applications and document lessons learned. | BCP/IT
Recover | Recovery Communication | RC.CO-03 | Recovery activities are communicated to stakeholders | Partially Implemented | Fully Implemented | Yes | Medium | Create stakeholder communication templates and escalation procedures for major outages. | BCP

## Project Scope
Project | NIST CSF 2.0 Cybersecurity Risk Assessment & Gap Analysis
Organization | Maple Financial Services (fictional)
Industry | Financial Services
Employees | 500
Assessment Objective | Assess cybersecurity posture, identify gaps, prioritize risks and develop remediation recommendations aligned to NIST CSF 2.0.
Scope | Customer-facing online banking platform, corporate IT, IAM, cloud infrastructure and protection of customer information.
Out of Scope | Physical security, non-IT business operations and detailed secure software development lifecycle assessment.
Methodology | NIST CSF 2.0 Core outcomes; Current/Target State Profile; qualitative 5x5 likelihood-impact risk scoring for this simulated exercise.
Important Note | All company information, evidence and assessment results are fictional and created for portfolio demonstration purposes.

## Risk Register
ID | Risk | Asset | Threat/Vulnerability | Likelihood | Impact | Score | Rating | Treatment | Owner | Recommended Action
R-001 | Unauthorized access to employee accounts | Employee identities / critical applications | Credential theft combined with inconsistent MFA | 4 | 5 | 20 | Critical | Mitigate | IAM | Implement phishing-resistant MFA and quarterly privileged access reviews.
R-002 | Customer data breach | Customer database | Incomplete encryption/control coverage | 3 | 5 | 15 | High | Mitigate | Security | Verify encryption coverage and strengthen database access monitoring.
R-003 | Ransomware disruption | Cloud and corporate infrastructure | Incomplete monitoring and recovery testing | 3 | 5 | 15 | High | Mitigate | IT/Security | Expand monitoring and conduct recovery exercises for critical services.
R-004 | Third-party security incident | SaaS vendors | Inconsistent vendor risk assessment process | 3 | 4 | 12 | High | Mitigate | GRC | Implement standardized third-party security assessments and risk tiering.
R-005 | Delayed incident detection | Critical IT systems | Incomplete centralized logging | 3 | 4 | 12 | High | Mitigate | SOC | Centralize logs and establish alert triage SLAs.
R-006 | Excessive user privileges | Business applications | Infrequent access certification | 4 | 4 | 16 | High | Mitigate | IAM | Implement quarterly access certifications and least-privilege reviews.
R-007 | Asset visibility gaps | IT/cloud assets | Incomplete asset inventory | 3 | 4 | 12 | High | Mitigate | IT | Create and maintain a centralized asset inventory.
R-008 | Delayed regulatory reporting | Customer and regulatory data | Unclear escalation/reporting ownership | 2 | 4 | 8 | Medium | Mitigate | Legal/Security | Document reporting obligations and incident escalation paths.

## Remediation Plan
Risk ID | Action | Owner | Priority | Target Window | Status
R-001 | Implement phishing-resistant MFA | IAM | Critical | 0-90 days | Open
R-006 | Implement quarterly access certification | IAM | High | 0-90 days | Open
R-002 | Verify encryption coverage for critical data stores | Security | High | 0-90 days | Open
R-007 | Create centralized asset inventory | IT | High | 0-90 days | Open
R-003 | Expand monitoring and test recovery | IT/Security | High | 31-120 days | Open
R-004 | Implement standardized third-party risk assessment | GRC | High | 31-120 days | Open
R-005 | Centralize logging and define alert SLAs | SOC | High | 31-120 days | Open
R-008 | Document regulatory incident reporting workflow | Legal/Security | Medium | 61-120 days | Open

## Executive Dashboard
NIST CSF 2.0 Executive Risk Dashboard
Assessment Metrics |  | Risk by Rating
Total Assessed Outcomes | 21 | High | 6
Identified Gaps | 18 | Critical | 1
Critical Risks | 1 | Medium | 1
High Risks | 6
Medium Risks | 1
Low Risks | 0

## Methodology
Step | What You Did
1. Scope | Defined the fictional organization, business services, technology environment and assessment boundaries.
2. Select Outcomes | Selected relevant NIST CSF 2.0 outcomes across Govern, Identify, Protect, Detect, Respond and Recover.
3. Current Profile | Documented the simulated current cybersecurity practices and evidence assumptions.
4. Target Profile | Defined the desired cybersecurity outcomes based on business risk and reasonable control expectations.
5. Gap Analysis | Compared current and target states to identify control/practice gaps.
6. Risk Assessment | Converted material gaps into risks and scored likelihood x impact using a 5x5 qualitative methodology.
7. Treatment | Assigned risk treatment and recommended remediation actions.
8. Reporting | Created an executive dashboard and remediation roadmap for leadership.
Portfolio Note | This is a simulated project. Do not represent fictional findings as professional client work.